VOLUME 2

# SECTION 3:
SPECIAL CONDITIONS

- CONTENTS

Article 2:          Law and language of the contract

Article 3: 	Order of precedence of contract documents

Article 4:	Communications

Article 5:	Supervisor and Supervisor's representative

Article 8:	Documents to be provided

Article 9:	Access to the site

Article 12:       General obligations of the Contractor

Article 15:	Performance guarantee

Article 16:	Insurance

Article 17:	Programme of implementation of tasks

Article 19:	Contractor's drawings

Article 20:	Sufficiency of tender prices

Article 24:        Interference with traffic

Article 27:	Demolished materials

Article 30:	Soil studies

Article 34:	Period of implementation of tasks

Article 36:	Delays in implementation of tasks

Article 39:	Work register

Article 40:	Origin and quality of works and materials

Article 43:	Ownership of plant and materials

Article 44:	General principles for payments

Article 46:	Pre-financing

Article 47:	Retention monies

Article 48:	Price revision

Article 49:	Measurement

Article 50:	Interim payments

Article 51:	Final statement of account

Article 53:	Delayed payments

Article 61:	Defects liability

Article 68:	Dispute settlement

- Article 2: 	Law and language of the contract

2.1	Community law is the law which applies to the contract, complemented, where necessary, by Belgian law.

2.3	The language used shall be English.

- Article 3: 	Order of precedence of contract documents

The following documents shall be deemed to form and be read and construed as part of this contract, in the following order of precedence:

(a) the contract,

(b) the Special Conditions,

(c) the General Conditions,

(d) the technical specifications,

(e) the design documentation (drawings),

(f) the priced bill of quantities (after arithmetical corrections)/price breakdown,

(g) the tender with the appendix,

(h) any other document forming part of the contract.

- Article 4:	Communications

Any written communication relating to this Contract between the Contracting Authority and/or the Supervisor, on the one hand, and the Contractor, on the other, must state the Contract title and contract number, and must be sent by post, fax, e-mail or by hand to the following addresses:

For the Contracting Authority:

| Name: | Delegation of the European Commission to the Republic of Serbia, Attn: _____________ |
| --- | --- |
| Address: | Vladimira Popovica 40 GTC Avenue block 19a 11070 New Belgrade, Republic of Serbia |
| Telephone: |  |
| Fax: |  |

For the Contractor:

| Name: |  |
| --- | --- |
| Legal Address: |  |
| Telephone: |  |
| Fax: |  |
| Legal form: |  |
| Nationality: |  |
| Registered number of VAT: |  |
| Registered number in the Chamber of Commerce / Commercial Court |  |

- Article 5:	Supervisor and Supervisor's representative

5.3	The Supervisor acts for the Contracting Authority. He has no authority to relieve either party of any duties, obligations or responsibilities under the Contract. Any approval, check , certificate, consent, examination, inspection, instruction, request, test or similar act by the Supervisor (including absence or disapproval) shall not relieve the Contractor from any responsibility he has under the Contract, including the responsibility for errors, omissions, discrepancies and non-compliance.

Any failure to disapprove any work, plant or material shall not constitute approval, and shall therefore not prejudice the right of the Supervisor to reject the work, plant or material.

5.4 	For any changes, the Supervisor shall check proposal from Contractor and give advice to the Contracting Authority regarding preparation of the formal addendum to contract.

The following types of changes needs to be introduced throw formal addendum:

A.	Changes with technical impact that modify the scope of works as defined in the Technical Specification;

B.	Changes with financial impact that lead to an increase in the total contract price, such that it is not longer covered by the original contract value.

C. Changes of the contractual essence, such as changes in the conditions of contract, contract agreement, appendix to tender  or other such parts of the contract.

D. Changes related to the extension of contract duration.

- Article 8:	Documents to be provided

8.3	The Supervisor, where necessary and/or appropriate shall ask the Contractor to prepare for his approval:

- Such design drawings specifications and calculations as shall be necessary to satisfy the Municipality in order to obtain their approval for use/occupation, in the language required from that Municipality.

- Operation and maintenance manuals together with As-Built drawings of the Permanent Works as completed (3 hard copies plus an electronic version), shall be provided in Serbian and English in sufficient detail to enable the Beneficiary to operate, maintain, dismantle, reassemble and adjust the Permanent Works incorporating that design.  The works shall not be considered to be completed for the purpose of taking over in accordance with Art. 60 until such operation and maintenance manuals, together with As-Built drawings on completion, have been submitted to, and approved by  the Supervisor

- Article 9:	Access to the site

9.1	The Contractor’s attention is drawn to the fact that there is a Head of Delegation of the European Commission in the state of the Contracting Authority. The Contractor is bound to give the Head of Delegation free access to its sites, factories, workshops, etc., and generally assist the Head of Delegation, like the project Supervisor, in the performance of his duties. The same provisions also apply to the appointed representatives of the Head of Delegation.

All correspondence between the Contractor and the Contracting Authority or project Supervisor must be copied, for information, to the Head of Delegation of the European Commission at the following official address:

Delegation of the European Commission to the Republic of Serbia,

Avenija 19a Building, Vladimira Popovica 40/V,

11070 New Belgrade, Republic of Serbia

Tel: +381 11 308 32 00

Fax: +381 11 308 3201

Article 12:	General obligations of the Contractor

12.8	The visibility measures must comply with the rules laid down in the Communication and Visibility Manual for EU External Actions published by the European Commission: http://ec.europa.eu/europeaid/work/visibility/index_en.htm.

- Article 15:	Performance guarantee

15.1	The amount of the performance guarantee shall be 10% of the amount of the Contract and any addenda thereto.

- Article 16:	Insurance

16.4	The amount of insurance covering liability with regard to risks and civil liability insurance shall be unlimited for an amount of 1 M€. This insurance will also be required to cover all subcontractors, unless similiar insurance has been taken out by the subcontractors

- Article 17:	Programme of implementation of tasks

17.1	The Contractor shall submit to the Supervisor an Implementation Programme in Critical Path Analysis format.

The programme shall reflect any specific requirements set out in the Contract Documents and Contractor's Tender, giving details on:

a)	the list of sub-contractors he proposes to employ on the Works together with details of the part of the Works he proposes to subcontract;

b)	the schedule of key personnel and organisation chart;

c)	the schedule of sources of materials, plant and equipment for incorporation into the works;

d)	milestones for all mayor groups of works etc.

The Programme and Schedule shall be submitted in hard copy and electronic format. Programme shall take into account the appropriate time needed for purpose of informing public regarding closing the roads and streets or for limiting or disconnecting water, electricity or other utilities.

- Article 19:	Contractor's drawings

19.1	 On the basis of the Specifications, Drawings and other information contained in the Tender Documents, the Contractor shall supply all further fabrication and working drawings, documents, calculations, official permits and other data necessary for the construction of the Works and for satisfying the technical parameters stipulated in the Contract. The Contractor may supply this information successively in parts, but each part submitted should be complete to such an extent that it can be judged and approved by the Supervisor in isolation as part of the whole.

The Supervisor may instruct the Contractor to prepare particular drawings or to make any modifications, including calculations for any part of the project. These calculations and drawings are part of the Contractor’s duties.

19.7	The language of the manuals and drawings will be Serbian language.

- Article 20:	Sufficiency of tender prices

20.1	Throughout the construction of the Works the Contractor shall provide and maintain for the site staff appropriate offices, stores, dining rooms, sanitary and health and safety facilities etc. All operating and maintenance expenses connected therewith (lighting, heating, water supply etc.)  shall be borne by the Contractor. The Contractor may require land outside the Site for his offices, stores, workshops, fabrication plants etc, The expenses and other costs so incurred shall be at the expense of the Contractor.

Article 24:	Interference with traffic

24.2	 No important operation of any kind, especially cutting through, transit over, or closing existing roads, water conduits or other public utility shall be carried out without the written consent of the Supervisor.

The Contractor shall inform the Supervisor in due time which shall be not less than 7 calendar days in writing before commencing such works in order that the Supervisor may arrange adequate supervision and safety precautions. With his application for permission to start construction work, the Contractor shall submit to the Supervisor a list of all major plant he and his sub-contractors intend to use, indicating their characteristics (Excavators, trucks, cranes, compaction equipment, rollers, concrete mixers, equipment, etc.).

- The Contractor shall select routes, choose and use such vehicles and restrict and distribute loads in such a way to prevent damage to the roads or structures communicating with or on the routes to the Site. The Contractor shall ensure that roads and bridges that have become damaged due to the Contractor’s use of that infrastructure, in the opinion of the Supervisor, are reinstated to a serviceability level similar to that which existed prior to the Contractor’s use of the infrastructure. Reinstatement shall be to the approval of the Supervisor. All expenses related to these procedures shall be covered by the Contractor.

- Article 27:	Demolished materials

27.1	 No material to be removed from the site as result of demolition, dislocations etc. will become the property of the Contracting Authority. Should some material be of interest to the Beneficiary, the demolished materials will become the property of the Beneficiary.

The contractor will be responsible for removal of the demolition material.

- Article 30:	Soil studies

30.1	 The Contractor shall bear all costs of the manpower and equipment used for any soil survey that may be necessary for the undisturbed project execution.

- Article 34:	Period of implementation of tasks

34.1	The period of implementation of tasks specified in the Appendix to Tender shall, without prejudice to extensions of the period of implementation of the tasks which may be granted under Article 35, commence on the date fixed in accordance with Article 33. The Period of implementation of tasks shall include mobilisation, implementation programme and/or design as required and the completion of execution of the works.

- Article 36:	Delays in implementation of tasks

36.1	The rate of liquidated damages for delays in the completion of works shall be 0.1% of the contract price for every day or part thereof which elapses between the end of the period of implementation of tasks and the actual date of completion, up to a maximum amount of 10% of the contract price or, if the contract is subdivided into phases, 10% of the price of the phase concerned.

- Article 39:	Work register

In the first paragraph of Article 39.1 replace the word”Supervisor” with word ”Contractor”

39.2	The statements shall be prepared by the Contractor, in accordance with the Specifications and the Bill of Quantities respectively. The statements shall be two separate documents, one for quality control and one for quantitative measurement. The documents shall be permanently kept at the site, in hard copy and in electronic format. The Contractor shall measure, in cooperation with the Supervisor’s staff, and prepare records of the work executed in such detail as instructed by the Supervisor.

39.3	The records shall be made in one original and at least two copies of which the original and first copy shall be submitted to the Supervisor for approval. If the Supervisor does not agree to the records, the Contractor shall be so advised, as quickly as possible and in any case within 14 days, of receiving the records, and a joint measurement or inspection shall be carried out. In case the parties can not agree on the joint measurements or inspections, the records made by the Supervisor shall be deemed to be correct.

- Article 40:	Origin and quality of works and materials

## 40.1	All supplies and material to be incorporated in or required for the works must originate in a Member States of the European Union or in a country or territory of the regions covered and/or authorised by the specific instruments applicable to the IPA programme under which the contract is financed. For these purposes, "origin" means the place where the materials and/or equipment are mined, grown, produced or manufactured and/or from which services are provided. The origin of the goods shall be determined according to the rules laid down in the Community Customs Code or the international agreements to which the country concerned is a signatory.

When importing goods, any change in the specified origin must have been pointed out to the project Supervisor and approved by him.

40.2	The works and the objects, appliances, equipment or materials used in their construction must comply with the specifications and the particular requirements of the technical document(s) detailed in Volume 3 of the Tender Dossier.

- Article 43:	Ownership of plant and materials

43.2	Equipment and materials intended for incorporation in the permanent works, but not yet incorporated in the permanent works and for which any interim payment has been made by the Contracting Authority, shall be vested in the Contracting Authority and visibly marked as such.

- Article 44:	General principles for payments

44.1	Payments shall be made in euro.

44.3	By derogation the payment to the Contractor of the amounts due under each of the interim payment certificates and the final statement of account issued by the Supervisor shall be made by the Contracting Authority within 45 days.

- Article 46:	Pre-financing

46.(1) 	The total amount of the pre-financing will be 10% of the original contract price.

In order to obtain the pre-financing payment, the Contractor must provide the Contracting Authority with a financial pre-financing guarantee for the full amount of the pre-financing payment.

46.8	The repayment of the pre-financing shall take the form of deductions of 15% of the amount of the paid pre-financing from each Interim payment certificate.

- Article 47:	Retention monies

47.1	The sum to be retained from interim payments to guarantee implementation of the Contractor's obligations during the maintenance period is 10% of each instalment.

- Article 48:	Price revision

  - Prices contained in the Contractor's tender (volume 4, section Detailed breakdown of prices) shall be deemed to have been established at the economic conditions in force 30 days prior the latest date fixed for  the submission of the tenders (reference date). If there is a variation in the economic conditions during the works, the monthly interim certificate of payment will be adjusted by applying the revision formulas in accordance with article 48.2.

  - The revision of prices shall be calculated by combining the application of (a) proportional formula and (b) mono-material formula for cement, bitumen and reinforced steel as follows:

(a)	the revision of prices shall be calculated by applying the following proportional formula to the amount of each interim certificate of payment after deduction of any amount due for repayment of pre-financing:

P = Po [(a + b (EnEo x 1+CHn1+CHox  TxoTxn ) + c MtnMto + d (xTxoTxn) - 1]

Where:

P=	upwards or downwards price revision of the interim certificate of payment for the period "n" concerned.

Po=	amount of the interim certificate of payment after deduction of any amount due for repayment of pre-financing.

- Eo=	official daily pay of the working team <specify the team composition by category> in Serbia at the reference date:

- En=	official daily pay of the working team <specify the team composition by category> in Serbia at the month n

- CH0:	percentage of increase in social contributions for a worker's pay resulting from the application of the laws and regulations in force in Serbia at the reference date.

- CHn:	same index but at the month n.

- Mt0:	official index for the supply and maintenance of fixed and moving parts of construction plant, including vehicles, machines, tools and spare parts necessary for civil engineering works, as published by <specify the selected indices' source and editor>.

- Mtn:	same index but in month n.

- G0:	pump price of diesel recorded in Serbia at the reference date (excluding taxes if the contract is tax and duty free).

- Gn:	same price but at the month n (excluding taxes if the contract is tax and duty free).

Txo:	exchange rate between the currency of contract payment and the currency of the selected indicator at the reference date.

Txn:	same exchange rate at the month n.

- The coefficients a, b, c and d shall be set by the Contractor on the basis of the detailed breakdown of prices as submitted in its tenders. The Contractor will have to provide clear arithmetical calculations for the proposed coefficients. The total of the coefficients must be equal to 1.

- (b)	the revision of prices for cement, bitumen and reinforced steel shall be calculated by applying the following mono-material formula separately, to each of the components:

Dm = Qn C x (Matn/Txn  –  Mat0/Tx0)

Dm=	increase or decrease to be paid for the material concerned by the revision of prices during the month "n".

Qn=	quantity of works carried out during the month n involving one or more of the materials in question.

C=	coefficient of transformation allowing to calculate the quantity of material used in the quantity of works carried out Qn.

The value of coefficient C is defined as follows:

- for cement, the coefficient C is expressed in tonnes for each cubic metre of concrete executed as per category specified in the contract;

- for reinforcing steel, the coefficient C is expressed in tonnes of steel laid for each cubic metre of reinforced concrete executed in accordance with the plans of reinforcement;

- for bituminous mixtures, the C coefficient is expressed in tonnes of bitumen 60/70 grade for tons of bituminous mixture executed.

Mat0=official supply price of the concerned material at the reference date.

Matn=official supply price of the concerned material at the month n.

Txo=	exchange rate between the currency of contract payment and the currency of the material's country of origin at the reference date.

Txn:	exchange rate betweend the currency of contract payment and the currency of the material's country of origin at the month n.

- (c)	there will be no revision treshold;

(d)	If the Contractor modifies the country of origin of the source of its materials or other components to be used for the execution of works, it shall inform by writing within 30 days the Supervisor, who will change the formula for the revision of prices by introducing the indices of the new country of origin.

- Article 49:	Measurement

49.1		This is a unit-price contract.

- Article 50:	Interim payments

50.1	 The Contractor shall submit an application for interim payment to the Supervisor at the end of each month in a form approved by the Supervisor. The application shall include the following items, as applicable:

a)	the estimated Contract value of the permanent Works executed up to the end of the  period in question, in hard copy and in electronic format, calculated in accordance with  procedure laid down in Article 49.

b) 	  an amount to be withheld as retention monies under of Article 47;

c) 	an amount to be deducted on account of the Prefinancing repayment under the provisions of Article 46;

d)    any other sum to which the Contractor may be entitled under the Contract

The minimum amount of  interim payment certificate shall be 350,000 Euro.

- Article 51:	Final statement of account

51.1	Not later than 90 days before the issue of the Final Acceptance Certificate, the Contractor shall submit to the Supervisor a draft final statement of account with supporting documents showing in detail the value of the work done in accordance with the Contract, together with all further sums which the Contractor considers to be due to him under the Contract in order to enable the Supervisor to prepare the final statement of account. The Supervisor shall make comments and/or objections concerning the draft final statement supplied by the Contractor within twenty eight days of their submission and these comments and/or objections shall be considered as accepted by the Contractor should he not contradict them in writing, delivered to the Supervisor, within twenty eight days of their receipt

- Article 53:	Delayed payments

53.1	Once the deadline laid down in Article 44.3 of the General Conditions has expired, the Contractor shall receive late-payment interest:

-	at the rate applied by the European Central Bank to its main refinancing transactions in euro where payments are in euro,

-	at the rediscount rate applied by the central bank of the beneficiary country if payments are in the currency of that country,

on the first day of the month in which the deadline expired, plus three and a half percentage points. The late-payment interest shall apply to the time which elapses between the date of the payment deadline, and the date on which the Contracting Authority’s account is debited. By way of exception, when the interest calculated in accordance with this provision is lower than or equal to EUR 200, it shall be paid to the Contractor only upon a demand submitted within two months of receiving late payment. The Member States are not entitled to late-payment interest.

- Article 61:	Defects liability

61.1	As stated in the glossary of terms in general annexes, the defects liability period is defined as the period stated in the contract immediately following the date of provisional acceptance, during which the Contractor is required to complete the works and to remedy defects or faults as instructed by the Supervisor. The rights and obligations of the parties with regard to this defects liability period are laid down in Article 61 of the General Conditions.

- Article 68:	Dispute settlement

68.4

Any dispute arising out of or relating to this contract which cannot be settled otherwise shall be referred to the exclusive jurisdiction of the courts of Brussels, Belgium.

- Article 73:	Further additional clauses

73.1	Vehicles for the Supervisor:

The Contractor shall provide the Supervisor with two (2) new cars as specified in the Bill of Quantities. Vehicles shall be delivered (with registration plates, vehicle license, and be comprehensively insured) prior to the Commencement of works on site. The Contractor shall be responsible for provision of fuel, lubricants, servicing, repair, maintenance and comprehensive insurance of the vehicles of the Supervisor. In the case of accidental damage, the Contractor shall be responsible for reinstatement of the damaged vehicle to its original condition. The Contractor shall supply temporary replacement vehicle during periods when the car is immobilized.

These costs are considered to be included in items of the Bill of Quantities and shall not be charged separately.

The ownership of all office equipment and all vehicles shall be transferred to the Beneficiary after Taking Over