25 December 2014

WEEKLY COMMUNICATIONS UPDATE

Overview

- Twelve new houses in Obrenovac, Krupanj, Paraćin and Mionica have been constructed so far, while 429 flood affected homes have been renovated in Obrenovac, Krupanj, Smederevska Palanka,Velika Plana, Čačak, Ub, Jagodina, Paraćin, Osečina, Šabac, Bajina Bašta, Šid, Loznica and Mionica. During the next week, the completion of 28 new houses is expected, while 185 reconstructions shall be finalized. The private housing reconstruction process for the total of some 950 in 30 municipalities funded through the European Union Assistance for Flood Relief in Serbia Programme is underway. Depending upon the weather conditions, the completion of this intervention is expected during December 2014,  January and February 2015.

- Delivery of animal feed to some 1,600 agriculture producers in 24 municipalities started on 23 December 2014 and it will continue throughout January 2015. Beneficiaries will receive 320 kilograms of animal feed for cows, pigs and layers.

Date of Update: 24th of December 2014

Implementing Partner: ASB/HC/IDC/DIVAC

| MUNICIPALITY | DESCRIPTION OF ACTION WITH OUTPUT AND STAGE OF COMPLETION AND TENTATIVE PLAN FOR THE NEXT WEEK | EXPECTED OUTCOME FOR END BENEFICIARIES INCLUDING THE END TIMEFRAME** |
| --- | --- | --- |
| Valjevo | Housing Component Reconstruction and building of new houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) 16 Housing Units reconstruction: Works on 14 houses are in finishing phase, in 2 houses are in progress Finishing of reconstruction works planned within approx 1 week. 9 new brick Housing Units: 3 houses are in construction, 5 houses are in preparation phase and in 1 house works did not start yet. Due to the weather conditions (snow) the houses will not be completed by the end of this year. Signing of the contract for furniture and appliances after the prior approval of DEU and preparation of distribution procedures Economic Component Distribution of IG Grants ongoing Plan for the next week Continue distribution of IG Grants | Housing Component Construction and reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) Building material 14-30.11 tender publication, evaluation and signing of the contract with best supply provider 01.12 starting of distribution of building material grants |
| Osecina | Housing Component Reconstruction of houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) 25 Housing Units reconstruction: works on 15 houses are finished, in progress 10 houses (80% of works are done) Finishing of reconstruction works planned within approx 1 week. Signing of the contract for furniture and appliances after the prior approval of DEU and preparation of distribution procedures Economic Component Distribution of IG Grants ongoing Plan for the next week Continue distribution of IG Grants | Housing Component Reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) Building material 14-30.11 tender publication, evaluation and signing of the contract with best supply provider 01.12 starting of distribution of building material grants |
| Mali Zvornik | Housing Component Reconstruction and building of new houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) 15 Housing Units reconstruction: Works on 13 houses are in finishing phase, in 2 houses are in progress. Finishing of reconstruction works planned within approx 1 week. 1 new Housing Unit: House is in finishing phase, interior works and setting the laminate still to be done All interior installations are done Finishing of construction works planned within approx 3 – 4 weeks. Signing of the contract for furniture and appliances after the prior approval of DEU and preparation of distribution procedures Economic Component Distribution of IG Grants ongoing Plan for the next week Continue distribution of IG Grants | Housing Component Construction and reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) Building material 14-30.11 tender publication, evaluation and signing of the contract with best supply provider 01.12 starting of distribution of building material grants |
| Ljubovija | Housing Component Reconstruction and building of new houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) 17 Housing Units reconstruction: Works on 12 houses are in finishing phase, in 5 houses are in progress (80% of works are done) Finishing of reconstruction works planned within approx 1 week. 6 Housing Units construction: works are ongoing Finishing of construction works planned within approx 3 – 4 weeks. Signing of the contract for furniture and appliances after the prior approval of DEU and preparation of distribution procedures Economic Component Distribution of IG Grants ongoing Plan for the next week Continue distribution of IG Grants | Housing Component Construction and reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) Building material 14-30.11 tender publication, evaluation and signing of the contract with best supply provider 01.12 starting of distribution of building material grants |
| Sabac | Housing Component Reconstruction of houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) 27 Housing Units reconstruction: works on 12 houses are finished, finishing phase on 15 houses (90 - 95% of works are done) Finishing of reconstruction works planned within approx the end of the week. 1 new Housing Unit construction: works are ongoing Finishing of construction works planned within approx 1 month. Signing of the contract for furniture and appliances after the prior approval of DEU and preparation of distribution procedures Economic Component Distribution of IG Grants ongoing Plan for the next week Continue distribution of IG Grants | Housing Component Reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) |
| Bajina Basta | Housing Component Reconstruction and building of new houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) 22 Housing Units reconstruction: works on 18 houses are finished; 4 houses are in finishing phase (95% of works are done, the laminate still to be done), finishing planned by the end of the week; 5 Housing Units construction: Construction of 5 houses is in finishing phase, interior works and setting the laminate still to be done All interior installations are done. Finishing of 5 houses by the end of this week Signing of the contract for furniture and appliances after the prior approval of DEU and preparation of distribution procedures Economic Component Distribution of IG Grants ongoing Plan for the next week Continue distribution of IG Grants | Housing Component Construction and reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) Building material 14-30.11 tender publication, evaluation and signing of the contract with best supply provider 01.12 starting of distribution of building material grants |
| Sid | Housing Component Reconstruction and building of new houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) 22 Housing Units reconstruction: Works on 2 houses are finished; works on 12 houses are in finishing phase (90%); works on 8 houses are in progress (80%); Finishing of houses planned within approx 3-4 weeks 5 Housing Units construction: Construction of 1 house is in finishing phase; 4 houses are in progress. Finishing of houses planned within approx 2 weeks Signing of the contract for furniture and appliances after the prior approval of DEU and preparation of distribution procedures Plan for the next week complete construction works | Housing Component Construction and reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) |
| Loznica | Housing Component Reconstruction and building of new houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) -20 Housing Units reconstruction: Works on 5 houses are finished (without setting laminate); Works in finishing phase on 12 houses ( 95% of works are done); Works on 3 houses are in progress ( 70%) Finishing of houses planned within approx 2 weeks 9 Housing Units construction: 4 houses got the roof and for 2 houses all material is delivered; start of the construction of 3 new houses 6 houses planned for finishing by the half of January 2015; 3 houses to be completed in February 2015 Signing of the contract for furniture and appliances after the prior approval of DEU and preparation of distribution procedures Economic Component Distribution of IG Grants ongoing Plan for the next week Continue distribution of IG Grants | Housing Component Construction and reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) Building material 14-30.11 tender publication, evaluation and signing of the contract with best supply provider 01.12 starting of distribution of building material grants |

Date of Update: 24/12/2014

Implementing Partner: Danish Refugee Council – DRC with Eneca

| MUNICIPALITY | DESCRIPTION OF ACTION WITH OUTPUT AND STAGE OF COMPLETION AND TENTATIVE PLAN FOR THE NEXT WEEK | EXPECTED OUTCOME FOR FINAL BENEFICIARIES INCLUDING THE END TIMEFRAME |
| --- | --- | --- |
| Smederevska Palanka | Reconstruction of individual housing objects (DRC): Reconstruction process is nearing its completion. Tentative plan for the next week: Finalizing works in 18 out of 20 houses and ongoing ; | 20 houses in the process of reconstruction, out of which 14 have been completely repaired and ready for the family move-in. A total of 18 out of 20 planned beneficiaries will move in by the end of year. |
|  | Construction of prefabricated houses (DRC): The construction and installation process is ongoing on all 3 planned prefabs in line with the action plan. Tentative plan for the next week: Advanced Installation works on two prefabs and completion of comprising elements for one prefab. | Two prefabs installed by the end of the year, one prepared for installation and finalized by the end of Jan 2015. |
|  | Provision of household appliances and furniture sets (DRC): Ongoing delivery of household appliances and furniture for reconstructed housing objects. Tentative plan for the next week: Further delivery of basic sects of furniture and household appliances. | Basic sets of furniture delivered to all 20 beneficiaries of reconstructed houses by the end of year. Basic sets of furniture delivered to all 3 prefab beneficiaries by 25 Jan 2015. |
|  | IGA component (Eneca): The tender opening session for the Local Open Tender for economic grants (below EUR 270.000) was held on 19 Dec 2014 and the evaluation process is ongoing. Tentative plan for the next week: Successful tenderers will be awarded contracts and start designing delivery plans. | The best quality suppliers contracted for 3 economic grants in Smederevska Palanka; Deliveries of business equipment to 3 business entities realized from mid January onwards. |
| Velika Plana | Reconstruction of individual housing objects (DRC): The reconstruction process has been finalized in all 12 housing objects. Tentative plan for the next week: Monitoring and supervision/handover of realized works. | All 12 houses fully reconstructed and supervision/ handover process realized by the end of year. |
|  | Provision of household appliances and furniture sets (DRC): Ongoing delivery of household appliances and furniture for reconstructed housing objects. Tentative plan for the next week: Further delivery of basic sects of furniture and household appliances. | Basic sets of furniture delivered to all 12 beneficiaries of reconstructed houses by the end of year. |
|  | IGA component (Eneca): The tender opening session for the Local Open Tender for economic grants (below EUR 270.000) was held on 19 Dec 2014 and the evaluation process is ongoing. Tentative plan for the next week: Successful tenderers will be awarded contracts and start designing delivery plans. | The best quality suppliers contracted for 2 economic grants in Velika Plana; Deliveries of business equipment to 2 business entities realized from mid January onwards. |
| Cacak | Reconstruction of individual housing objects (DRC): The reconstruction process has been finalized in all 13 out of 14 housing objects. Tentative plan for the next week: Monitoring and supervision/handover of realized works. | 14 houses reconstructed by the end of year. |
|  | Provision of household appliances and furniture sets (DRC): Ongoing delivery of household appliances and furniture for reconstructed housing objects. Tentative plan for the next week: Further delivery of basic sects of furniture and household appliances. | Basic sets of furniture delivered to all 14 beneficiaries of reconstructed houses by the end of year. |
|  | IGA component (Eneca): The tender opening session for the Local Open Tender for economic grants (below EUR 270.000) was held on 19 Dec 2014 and the evaluation process is ongoing. Tentative plan for the next week: Successful tenderers will be awarded contracts and start designing delivery plans. | The best quality suppliers contracted for 1 economic grant in Cacak. Deliveries of business equipment to 1 business entity realized from mid January onwards. |
| UB | Reconstruction of individual housing objects (DRC): The reconstruction process has been finalized in all 19 out of 23 housing objects. Tentative plan for the next week: Monitoring and supervision/handover of realized works. | 23 houses in the process of reconstruction, out of which 19 completely repaired and ready for the family proper habitation. A total of 21 out of 23 planned beneficiaries will move in by the end of year. Two remaining housing objects will be reconstructed in Jan 2015. |
|  | Provision of household appliances and furniture sets (DRC): The delivery of household appliance and furniture is in the preparatory phase. | Basic sets of furniture and household appliances provided to the priority beneficiary families by the end of Jan 2015. |
|  | IGA component (Eneca): The tender opening session for the Local Open Tender for economic grants (below EUR 270.000) was held on 19 Dec 2014 and the evaluation process is ongoing. Tentative plan for the next week: Successful tenderers will be awarded contracts and start designing delivery. | The best quality suppliers contracted for 20 economic grants in Ub. Deliveries of business equipment to 20 business entities realized from mid January onwards. |
| Koceljeva | Reconstruction of individual housing objects (DRC): The reconstruction process has been brought to the completion phase. Tentative plan for the next week: Monitoring and supervision/handover of realized works. | 25 houses in the process of reconstruction, out of which 20 completely repaired and ready for the family proper habitation. A total of 23 out of 25 planned beneficiaries will move in by the end of year, while 2 remaining housing objects will be reconstructed in Jan 2015 per beneficiaries’ personal request. |
|  | Provision of household appliances and furniture sets (DRC): The delivery of household appliance and furniture is in the preparatory phase. | Basic sets of furniture and household appliances provided to the priority beneficiary families by the end of Jan 2015. |
|  | IGA component (Eneca): The tender opening session for the Local Open Tender for economic grants (below EUR 270.000) was held on 19 Dec 2014 and the evaluation process is ongoing. Tentative plan for the next week: Successful tenderers will be awarded contracts and start designing delivery plans. | The best quality suppliers contracted for 4 economic grants in Koceljeva. Deliveries of business equipment to 4 business entities will be realized from mid January onwards. Rehabilitation facility works finalized on 1 business entity affected by floods. |
| Jagodina | Reconstruction of individual housing objects (DRC): The reconstruction process has been brought to the completion phase. Tentative plan for the next week: Monitoring and supervision/handover of realized works. | Out of the total 33 houses selected for the reconstruction component, 25 completely reconstructed and ready for the family proper habitation. |
|  | Construction of prefabricated houses(DRC): The construction site has been prepared and the administrative conditions have been realized enabling the commencement of construction works by the end of December 2014. | Preparation of prefab elements and installation finalized by the end of Jan 2015. |
|  | Provision of household appliances and furniture sets (DRC): The delivery of household appliances and furniture is in the preparatory phase. | Basic sets of furniture and household appliances provided to the priority beneficiary families by the end of Jan 2015. |
| Paracin | Reconstruction of individual housing objects (DRC): The reconstruction process has been brought to the completion phase. Tentative plan for the next week: Monitoring and supervision/handover of realized works. | Out of the total 43 houses selected for the reconstruction component, 33 completely reconstructed and ready for the family proper habitation. |
|  | Construction of prefabricated houses (DRC): The construction process is nearing the completion in the majority of houses. Tentative plan for the next week: Monitoring and supervision/handover of realized works. | Advanced phase of work completion and preparation of infrastructure connections in 7 out of 10 prefabs. Seven prefabs installed by the end of the year, three prepared for installation and finalized by the end of Jan 2015. |
|  | Provision of household appliances and furniture sets (DRC): The delivery of household appliances and furniture is in the preparatory phase. | Basic sets of furniture delivered to all 53 rehabilitated and prefab housing objects by 25 Jan 2015. |
|  | IGA component (Eneca): The tender opening session for the Local Open Tender for economic grants (below EUR 270.000) was held on 19 Dec 2014 and the evaluation process is ongoing. Tentative plan for the next week: Successful tenderers will be awarded contracts and start deliveries. | The best quality suppliers contracted for 24 economic grants in Paracin. Deliveries of business equipment to 24 business entities will be realized from mid January onwards. Rehabilitation facility works finalized on all 6 business entities which were affected by floods. |

WEEKLY COMMUNICATIONS UPDATE

Date of Update:	25  December 2014

Implementing Partner:	Help – Hilfe zur Selbsthilfe e.V.

Overview:

Reconstruction works:

Total budget available 780.000,00 EUR

Initially planned 120 beneficiaries to receive the sets of material and works have been raised to 145 flood affected family households, however due to the savings in procurement possible reconstruction for 10 more in Svilajnac (beginning of works in January) – total estimated 155 sets of reconstruction works.

Works on the first 51 houses (10 Kraljevo, 15 Lazarevac, 15 Svilajnac, 5 Trstenik and 6 Varvarin) are in the finishing phase: the interior door placement and flooring, deadline as of 25 December.

Works on 94 houses starting sequentially and will be finished in 50 calendar days.

Prefabricated houses: The works on 8 prefabricated houses in Svilajnac and 1 in Varvarin in the final phase, expected to be finished by the end of December possibly in January due to the flooring postponement.

Value of the works in progress 151.500,00 EUR.

Initially planned 15, total to be supported 20 houses (11 Svilajnac, 1 Varvarin, 1 Ljig, 3 Smederevo, 1 Prolom Banja, Kursumlija, 3 Lazarevac), also due to the savings in procurement.

The works on 8 prefabricated houses in Svilajnac and 1 in Varvarin are in the final phase, expected to be finished by the end of December, pending the connection to the infrastructure

Household appliances and furniture: Initially planned 135 beneficiaries, during the procurement procedure made savings, thus final number of furniture and appliances sets to be delivered is 175 beneficiaries. This figure includes 20 prefabricated houses beneficiaries, but not necessarily the beneficiaries of reconstruction works.  The furniture and appliances supplier’s company have been selected, pending contract signing, delivery period 60 days.

Income generation activities:

Tender procedure commenced, deadline for submission of offers is 12 January 2015.

Initially planned 108 beneficiaries, currently selected 160, final number of supported pending procurement procedure.

| MUNICIPALITY | DESCRIPTION OF ACTION WITH OUTPUT ANDa) STAGE OF COMPLETION AND b)TENTATIVE PLAN FOR THE NEXT WEEK | EXPECTED OUTCOME FOR END BENEFICIARIES INCLUDING THE END TIMEFRAME** |
| --- | --- | --- |
| KRALJEVO | Reconstruction works in value of 29.022.74 EUR for 10 houses in Kraljevo in the final phase of inner finishing works: installation of interior doors and flooring still in progress. Works on additional 8 houses have started. Procurement procedure of 20 furniture sets is in progress, delivery pending. Tender for IGA component published on 19 Dec. | At least 10 homes repaired and at least 10 families provided with the basic furniture and household appliances. At least 20 micro and small business provided with equipment, spare parts and business facilities renovated. |
| KOSJERIC | On 3 November 12 beneficiaries in Kosjeric, village Seca Reka received 39800 raspberry seedlings. Value of the assistance: cca 11.000,00 EUR (1313400 dinara). | At least 10 micro and small businesses supported by the raspberry seedlings, equipment spare parts and renovated business facilities. |
| LAZAREVAC | Reconstruction works on 15 houses in Lazarevac, in value of 38.020,81 EUR, from the first lot in the finishing phase, interior doors installation in progress, completion by 29 December. Procurement procedure of furniture in progress, delivery pending. Tender for IGA component published on 19 Dec. | At least 30 families provided with the construction material sets and priority works; at least 36 beneficiaries provided with the basic furniture and household appliances, at least 20 micro and small businesses supported with raspberry seedlings, spare parts for equipment and renovation of business facilities. |
| SVILAJNAC | Reconstruction works on 15 houses and 8 prefabricated houses in Svilajnac in the finishing phase, interior door installation on/from 24 Dec, pending: works on pavement, septic tank and inspection chamber from 20 December followed by the water and electricity connection. Works will not be finished until mid of January. Works on 22 houses begun, and the rest of 37 expected to begin in the fourth week of December. Procurement procedure of 77 furniture sets in progress, deliveries pending. Tender for IGA component published on 19 Dec. | At least 70 construction material sets with priority works delivered; At least 78 sets of basic furniture and household appliances supplied, eight families provided with the prefabricated houses; At least 23 micro and small businesses supported with raspberry seedlings, spare parts for equipment and renovation of business facilities. |
| TRSTENIK | Reconstruction works on 5 houses in the inner finishing phase, flooring and inner doors placement in progress. Launched works on 8 more houses to be finished by the end of January. Procurement procedure of 10 furniture sets in progress. Delivery pending. Tender for IGA component published on 19 Dec. | At least 5 households supported by the construction material sets with priority works, At least 5 households provided with the basic furniture and appliances sets, At least 15 micro and small businesses provided with raspberry seedlings, spare parts for equipment and renovation of business facilities. |
| VARVARIN | Reconstruction works on 6 houses in Varvarin in the finishing phase: flooring in progress and interior doors placement. All works expected to be finished by 29 December. Procurement procedure of 8 furniture sets in progress, pending delivery. Tender for IGA component published on 19 Dec. | At least 5 families supported by the construction material sets with priority works. At least 6 families supported by the basic furniture and household appliances. One family supported by provision of prefabricated house, At least 20 micro and small businesses supported with raspberry seedlings, spare parts for equipment and renovation of business facilities. |

Date of Update: 25 December 2014

Implementing Partner: UNOPS

| MUNICIPALITY | DESCRIPTION OF ACTION WITH OUTPUT AND STAGE OF COMPLETION AND TENTATIVE PLAN FOR THE NEXT WEEK | EXPECTED OUTCOME FOR END BENEFICIARIES INCLUDING THE END TIMEFRAME** |
| --- | --- | --- |
| 16 Local Self-Governments | The construction of nine houses in Obrenovac, Krupanj and Mionica is completed. The construction process on 59 houses is underway. This includes provision of 60, 80 and 100 square metres dwellings to the affected families. The completion of works is expected during Decemeber, January and February 2015. |  |

Date of Update: 25 December 2014

Implementing Partner: FAO

| MUNICIPALITY | DESCRIPTION OF ACTION WITH OUTPUT AND STAGE OF COMPLETION AND TENTATIVE PLAN FOR THE NEXT WEEK | EXPECTED OUTCOME FOR END BENEFICIARIES INCLUDING THE END TIMEFRAME** |
| --- | --- | --- |
| All 24 municipalities | Delivery of animal feed started on 23 December 2014 and it will continue throughout January 2015. Beneficiaries in 24 municipalities will receive 320 kilograms of animal feed each, based on their stated priorities they will receive feed for cows, pigs and layers. | In period December 2014 - mid-January 2015, animal feed will be delivered to more than 1,600 agriculture producers. |
| Smederevska Palanka | Animal feed delivery in Smederevska Palanka is completed on 23 December 2014. Delegation of the DEU , led by Mr. Michael Davenport, visited distribution warehouse where 53 producers received animal feed for cows, pigs and layers. | Smederevska Palanka will in future receive more support from the FAO. By the end of January, this municipality will, among other 24, receive spring crops seed. |
| All 24 municipalities | Tender for procurement of spring cropping season is launched. Potential vendors are invited to submit their bids with the deadline as 10 January 2015. More than 7,800 agriculture producers will receive spring crops seed (barley, peas, red clover, lucerne and maize). | Spring crops and fertilizer will be delivered to beneficiary families during the period early February till end of March 2015. In terms of number of beneficiaries, this will be the largest group receiving support under the EU flood recovery programme. |