15 January 2015

WEEKLY COMMUNICATIONS UPDATE

Overview

- Thirty-eight houses in Obrenovac, Krupanj, Svilajnac, Varvarin, Paraćin, Gornji Milanovac, Bajina Bašta, Šid and Mionica have been constructed, while 624 flood affected homes have been renovated in Obrenovac, Krupanj, Kraljevo, Lazarevac, Svilajnac, Trstenik, Varvarin, Valjevo, Mali Zvornik, Ljubovija, Šabac, Bajina Bašta, Šid, Loznica, Smederevska Palanka, Velika Plana, Čačak, Ub, Koceljeva, Jagodina and Paraćin. The construction works are in the finishing stage on some 65 family houses. This is the part of private housing reconstruction process for the total of some 950 in 30 municipalities funded through the European Union Assistance for Flood Relief in Serbia Programme which is well underway.

- The total of 1,614 agriculture producers in 24 municipalities hardest affected by the floods received packages animal feed in period 23 December – 16 January 2015. This included 516,800 kilograms of feed for cows, pigs and layers. Within the next stage of EU support to agriculture families, milking equipment will be delivered to 25 farms during February.

Date of Update: 15th of January 2015

Implementing Partner: ASB/HC/IDC/DIVAC

| MUNICIPALITY | DESCRIPTION OF ACTION WITH OUTPUT AND STAGE OF COMPLETION AND TENTATIVE PLAN FOR THE NEXT WEEK | EXPECTED OUTCOME FOR END BENEFICIARIES INCLUDING THE END TIMEFRAME** |
| --- | --- | --- |
| Valjevo | Housing Component Reconstruction and building of new houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) 16 Housing Units reconstruction: Works on 16 houses is completed and handover procedures started. 9 new brick Housing Units: Works on 2 houses are ongoing (preparation of the roof); works on 2 houses did not start yet and works on 5 houses have been stopped due to the weather conditions. Economic Component Distribution of IG Grants has been completed Plan for the next week Plan the distribution of furniture and appliances Monitor construction works and prepare handover procedures for reconstruction Monitor the distribution of IG Grants and building material | Housing Component Construction and reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) Building material 14-30.11 tender publication, evaluation and signing of the contract with best supply provider 01.12 starting of distribution of building material grants |
| Osecina | Housing Component Reconstruction of houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) 25 Housing Units reconstruction: Works on 15 houses completed; in 10 houses are in finishing phase and it will be completed by the end of January 2015, according to the weather conditions. Finishing of reconstruction works planned within approx 2 weeks. Economic Component Distribution of IG Grants completed Plan for the next week Plan the distribution of furniture and appliances Monitor reconstruction works and prepare handover procedure Monitor the distribution of IG Grants and building material | Housing Component Reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) Building material 14-30.11 tender publication, evaluation and signing of the contract with best supply provider 01.12 starting of distribution of building material grants |
| Mali Zvornik | Housing Component Reconstruction and building of new houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) 15 Housing Units reconstruction: Works on 15 houses is completed and handover procedures started. 1 new Housing Unit: Works are in finishing phase (90%), connection to the electrical network has been done; construction of septic tanks still needs to be done; the house will be completed by the end of January 2015. Finishing of construction works planned within approx 2 weeks. Economic Component Distribution of IG Grants completed Plan for the next week Plan the distribution of furniture and appliances Monitor construction works and start handover procedures for reconstruction Monitor the distribution of IG Grants and building material | Housing Component Construction and reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) Building material 14-30.11 tender publication, evaluation and signing of the contract with best supply provider 01.12 starting of distribution of building material grants |
| Ljubovija | Housing Component Reconstruction and building of new houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) 17 Housing Units reconstruction: Works on 17 houses is completed and handover procedures started. 6 Housing Units construction: Works are in finishing phase, connection to the electrical network and construction of septic tanks still needs to be done; the house will be completed by the end of January 2015. Finishing of construction works planned within approx 3 weeks. Economic Component Distribution of IG Grants completed Plan for the next week Plan the distribution of furniture and appliances Monitor construction works and start handover procedures for reconstruction Monitor the distribution of IG Grants and building material | Housing Component Construction and reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) Building material 14-30.11 tender publication, evaluation and signing of the contract with best supply provider 01.12 starting of distribution of building material grants |
| Sabac | Housing Component Reconstruction of houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) 27 Housing Units reconstruction: works on 26 houses are finished; works on 1 house will be finished soon due to huge humidity (setting the laminate still to be done). Finishing of reconstruction works planned within approx 2 week. 1 new Housing Unit construction: works are ongoing Finishing of construction works planned within approx 2 months, according to weather conditions. Economic Component Distribution of IG Grants is ongoing and it will be completed soon. Plan for the next week Plan the distribution of furniture and appliances Start handover procedures for reconstruction and prepare construction works Monitor the distribution of IG Grants and building material Complete distribution of IG Grants | Housing Component Reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) |
| Bajina Basta | Housing Component Reconstruction and building of new houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) 22 Housing Units reconstruction: Works on all houses are finished and handover procedures completed in 5 housing units. 5 Housing Units construction: Construction of 5 houses is finished: all houses are connected to the electrical network; construction of septic tanks still needs to be done. Finishing of construction works planned within approx 2 weeks. Economic Component Distribution of IG Grants completed Plan for the next week Plan the distribution of furniture and appliances Continue handover procedures for reconstruction and construction works Monitor the distribution of IG Grants and building material | Housing Component Construction and reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) Building material 14-30.11 tender publication, evaluation and signing of the contract with best supply provider 01.12 starting of distribution of building material grants |
| Sid | Housing Component Reconstruction and building of new houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) 22 Housing Units reconstruction: Works on 8 houses are finished; works on 14 houses are in finishing phase (Deadline for finishing of works moved due to weather conditions and humidity by the end of January). Finishing of houses planned within approx 2 weeks 5 Housing Units construction: Construction of 1 house is finished; on 4 remaining houses works are in finishing phase (the interior and facade still to be done), connection to the electrical network and construction of septic tanks still needs to be done; all houses will be completed by the end of January 2015. Finishing of houses planned within approx 2 weeks Plan for the next week Plan the distribution of furniture and appliances Monitor reconstruction and construction works | Housing Component Construction and reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) |
| Loznica | Housing Component Reconstruction and building of new houses works implementation and monitoring (engineer field visit/meetings with beneficiaries) 20 Housing Units reconstruction: Works on 19 houses are finished and handover procedures started; works on 1 house is in finishing phase (Deadline for finishing of works moved due to weather conditions and humidity by the end of January). Finishing of houses planned within approx 2 weeks 9 Housing Units construction: interior works are in progress, planned for finishing by the end of January due to weather conditions; 3 additional houses: for 2 houses concrete foundation and solid ground floor is made, and for 1 house works are in progress; all three planned for finishing approximately by March 15th. Economic Component Distribution of IG Grants almost completed Plan for the next week Plan the distribution of furniture and appliances Monitor reconstruction and construction works and start handover procedures Monitor the distribution of IG Grants and building material | Housing Component Construction and reconstruction 06.10 tender publication 16.10 deadline for sending of the offers 17-25.10 tender evaluation and signing of the contract From 30.10 works opening Furniture and Appliances 20.11-26.11 Collection of the offers 26.11 Deadline for sending of the offers 27.11-02.12 Offers evaluation and selection of the best offer 03-10.12 signing of the contract starting the delivering of furniture and appliances (after DEU prior approval) Economic Component IG Grants 20-30.10 Collection of the offers 30.10 deadline for sending of the offers 01-05.11 Offers evaluation and selection of the best offer 05-20.11 signing of the contract starting the delivering of IG grants (after DEU prior approval) Building material 14-30.11 tender publication, evaluation and signing of the contract with best supply provider 01.12 starting of distribution of building material grants |

Date of Update: 15/01/2015

Implementing Partner: Danish Refugee Council – DRC with Eneca

| MUNICIPALITY | DESCRIPTION OF ACTION WITH OUTPUT AND STAGE OF COMPLETION AND TENTATIVE PLAN FOR THE NEXT WEEK | EXPECTED OUTCOME FOR FINAL BENEFICIARIES INCLUDING THE END TIMEFRAME |
| --- | --- | --- |
| Smederevska Palanka | Reconstruction of individual housing objects (DRC): The reconstruction of 20 houses is in the completion phase. Tentative plan for the next week: Monitoring and supervision/handover of realised works. | 19 out of 20 houses completely reconstructed, while the remaining one will be finalised by the end of January 2015. |
|  | Construction of prefabricated houses (DRC): The construction and installation process is ongoing on all 3 planned prefabs in line with the action plan. Tentative plan for the next week: Advanced phase of interior works in two prefabs. | Two prefabs installed with ongoing internal painting and flooring works while the third one is in the process of installation (to be finalised by the end of Jan 2015). |
|  | Provision of household appliances and furniture sets (DRC): Monitoring of realised activities. Tentative plan for the next week: Monitoring of realised activities. | Basic sets of furniture and household appliances delivered to all 20 beneficiaries of reconstructed houses. Basic sets of furniture and household appliances delivered to 2 out of 3 prefab beneficiaries. |
|  | IGA component (Eneca): The ongoing evaluation process of submitted offers. Tentative plan for the next week: Successful tenderers will be awarded contracts and start designing delivery plans. | The best quality suppliers will be contracted for 3 economic grants in Smederevska Palanka; Deliveries of business equipment to 3 business entities realized from 20 January onwards. |
| Velika Plana | Reconstruction of individual housing objects (DRC): The reconstruction process finalized in all 12 housing objects. | All 12 houses fully reconstructed and supervision/ handover process realised. |
|  | Provision of household appliances and furniture sets (DRC): Monitoring of realised activities. Tentative plan for the next week: Monitoring of realised activities. | Basic sets of furniture and household appliances delivered to all 12 beneficiaries of reconstructed houses. |
|  | IGA component (Eneca): The ongoing evaluation process of submitted offers. Tentative plan for the next week: Successful tenderers will be awarded contracts and start designing delivery plans. | The best quality suppliers will be contracted for 2 economic grants in Velika Plana; Deliveries of business equipment to 2 business entities launched from 20 January onwards. |
| Cacak | Reconstruction of individual housing objects (DRC): The reconstruction process finalized in all 14 houses. Tentative plan for the next week: Monitoring of realised activities. | All 14 houses fully reconstructed and supervision/ handover process realised. |
|  | Provision of household appliances and furniture sets (DRC): Monitoring of realised activities. Tentative plan for the next week: Monitoring of realised activities. | Basic sets of furniture and household appliances delivered to all 14 beneficiaries of reconstructed houses. |
|  | IGA component (Eneca): The ongoing evaluation process of submitted offers. Tentative plan for the next week: Successful tenderers will be awarded contracts and start designing delivery plans. | The best quality suppliers will be contracted for 1 economic grant in Cacak; Delivery of business equipment to 1 business entity launched from 20 January onwards. |
| UB | Reconstruction of individual housing objects (DRC): The reconstruction of 23 houses is in the completion phase. Tentative plan for the next week: Monitoring and supervision/handover of realized works. | 21 out of 23 houses completely reconstructed, while the remaining two will be finalised by the end of January 2015. |
|  | Provision of household appliances and furniture sets (DRC): The delivery of household appliance and furniture is in the preparatory phase. | Basic sets of furniture and household appliances launched to the priority beneficiary families in the last weeks of Jan 2015. |
|  | IGA component (Eneca): The ongoing evaluation process of submitted offers. Tentative plan for the next week: Successful tenderers will be awarded contracts and start designing delivery plans. | The best quality suppliers will be contracted for 20 economic grants in Ub. Delivery of business equipment to 20 business entities launched from 20 January onwards. |
| Koceljeva | Reconstruction of individual housing objects (DRC): The reconstruction of 25 houses is in the completion phase. Tentative plan for the next week: Monitoring and supervision/handover of realized works. | 24 out of 25 houses completely reconstructed, while the remaining one will be finalised by the end of January 2015. |
|  | Provision of household appliances and furniture sets (DRC): The delivery of household appliance and furniture is in the preparatory phase. | Basic sets of furniture and household appliances launched to the priority beneficiary families in the last weeks of Jan 2015. |
|  | IGA component (Eneca): The ongoing evaluation process of submitted offers. Tentative plan for the next week: Successful tenderers will be awarded contracts and start designing delivery plans. | The best quality suppliers will be contracted for 4 economic grants in Koceljeva. Delivery of business equipment to 4 business entities launched from 20 January onwards. |
| Jagodina | Reconstruction of individual housing objects (DRC): The reconstruction of 33 houses is completed. Tentative plan for the next week: Monitoring and supervision/handover of realized works. | All 33 houses completely reconstructed. |
|  | Construction of prefabricated houses(DRC): The construction site has been prepared and the administrative conditions have been realized enabling the commencement of construction works by the end of January 2015. | Preparation of prefab elements and installation finalized from the end of Jan 2015 onwards. |
|  | Provision of household appliances and furniture sets (DRC): The delivery of household appliances and furniture is in the preparatory phase. | Basic sets of furniture and household appliances launched to the priority beneficiary families in the last weeks of Jan 2015. |
| Paracin | Reconstruction of individual housing objects (DRC): The reconstruction of 43 houses is in the completion phase. Tentative plan for the next week: Monitoring and supervision/handover of realized works. | 37 out of 43 houses completely reconstructed, while the remaining six will be finalised by the end of the following week. |
|  | Construction of prefabricated houses (DRC): The construction process of 9 houses is in the closing construction phase. Tentative plan for the next week: Advancement of interior works | 9 out of 10 houses installed and preparations for infrastructure connections in process. |
|  | Provision of household appliances and furniture sets (DRC): Ongoing delivery of household appliances for 53 reconstructed and constructed housing objects. Tentative plan for the next week: Delivery of furniture sets to 53 selected beneficiary households. | Basic sets of household appliances and basic furniture delivered to all 53 reconstructed and constructed houses in Paracin by the end of Jan 2015. |
|  | IGA component (Eneca): The ongoing evaluation process of submitted offers. Tentative plan for the next week: Successful tenderers will be awarded contracts and start designing delivery plans. | The best quality suppliers will be contracted for 24 economic grants in Paracin. Delivery of business equipment to 24 business entities launched from 20 January onwards. |

Date of Update:		15 January 2015

Implementing Partner:		Help – Hilfe zur Selbsthilfe e.V.

Overview:

Reconstruction works: 51 finished - handover meetings with the contractors in progress

Total budget available 780.000,00 EUR

Initially planned 120 beneficiaries to receive the sets of material and works have been raised to total estimated 160 sets of reconstruction works  to the flood affected family households, due to the savings in procurement.

Works on the first 51 houses (10 Kraljevo, 15 Lazarevac, 15 Svilajnac, 5 Trstenik and 6 Varvarin) have been in the process of handover/transfer by the contractor and will go throughout January for example: Lazarevac handover 15 houses on 30 Dec 2014, Svilajnac 15 houses handover 09  Jan, , Trstenik handover of the first 5 houses in the week 12 Jan followed by  Kraljevo and Varvarin).

Works on 94 houses starting sequentially and will be finished in 50 calendar days.

Prefabricated houses: Finished 9 houses in the process of connecting to the infrastructure – estimated transfer from 26 – 30 January 2015.

Initially planned 15, total to be supported 20 houses (11 Svilajnac, 1 Varvarin, 1 Ljig, 3 Smederevo, 1 Prolom Banja, Kursumlija, 3 Lazarevac), also due to the savings in procurement.

The works on 8 prefabricated houses in Svilajnac and 1 in Varvarin are in the final phase, connection to the local infrastructure in progress, expected to be finished by the end of January.

Works on 3 prefabs in Lazarevac and 3 aditional in Svilajnac have been commenced.

Household appliances and furniture: Initially planned 135 beneficiaries, during the procurement procedure made savings, thus final number of furniture and appliances sets to be delivered is 180 beneficiaries. This figure includes 20 prefabricated houses beneficiaries, but not necessarily the beneficiaries of reconstruction works.  The furniture and appliances supplier’s company have been selected, contracts signed, delivery period 60 days and will begin by the end of January.

Income generation activities:

Tender procedure finished, signing contracts with the suppliers in progress, begining of delivery in February.

Initially planned 108 beneficiaries, currently selected 168, final number of supported pending procurement procedure.

Date of Update: 8 Jan 2015

Implementing Partner: UNOPS

| MUNICIPALITY | DESCRIPTION OF ACTION WITH OUTPUT AND STAGE OF COMPLETION AND TENTATIVE PLAN FOR THE NEXT WEEK | EXPECTED OUTCOME FOR END BENEFICIARIES INCLUDING THE END TIMEFRAME** |
| --- | --- | --- |
| 16 Local Self-Governments | The construction of 20 houses in Obrenovac, Gornji Milanovac, Krupanj and Mionica is completed. The construction process on 46 houses is well underway. This includes provision of 60, 80 and 100 square metres dwellings to the affected families. The completion of works is expected during January and February 2015. |  |
| Trstenik | The rehabilitation of three filtration lakes which provide water supply to 15,000 inhabitants of Trstenik is underway. This includes removal of the mud, regulation of the banks and placement of new layers of filtration sand. Rehabilitation of one lake is fully completed, while the works are well in progress on other two. The completion of this intervention funded by the EU with some 192,000 Euros is expected during February 2015. |  |

Implementing Partner: IOM

| MUNICIPALITY | DESCRIPTION OF ACTION WITH OUTPUT AND STAGE OF COMPLETION AND TENTATIVE PLAN FOR THE NEXT WEEK | EXPECTED OUTCOME FOR END BENEFICIARIES INCLUDING THE END TIMEFRAME** |
| --- | --- | --- |
| Krupanj | About 0.2 M investments. Out of 198 houses 165 repaired by IOM. 33 finished by the beneficiaries themselves. Cleaning and complaint works underway. | Commencement of the works in the first week of October. 198 houses to be repaired, but some houses already in the meantime finished by the beneficiaries themselves. Deadline: 50 days from the commencement of the works |
| Obrenovac | Over 0.5M EUR investment. All 110 houses in Obrenovac settlement Brace Jugovic are repaired and prepared for the Winter period at the end of December, except those with large damages that have been assessed by the Floods Office and re-categorized into category 6. Finishing works underway. Selection of the additional up to 40 beneficiaries underway. | Commencement of the works in the first week of October. Total of 110 houses, small and medium repairs. Deadline: 83 days from the commencement of the works. Additional houses to be selected for small and medium repairs. The municipality Obrenovac sent the list of 90 households; up to 40 houses to be selected for the most vulnerable families for repairs. |
| Obrenovac, Lazarevac temporary shelters | Equipment for the temporary shelter has almost been delivered in total. Additional measures taken in order to ensure the safety of the installed equipment. Living conditions improved for the Winter start. | Temporary shelters’ living conditions improved before the winter in both Lazarevac and Obrenovac. |

Date of Update: 15 January 2015

Implementing Partner: FAO

| MUNICIPALITY | DESCRIPTION OF ACTION WITH OUTPUT AND STAGE OF COMPLETION AND TENTATIVE PLAN FOR THE NEXT WEEK | EXPECTED OUTCOME FOR END BENEFICIARIES INCLUDING THE END TIMEFRAME** |
| --- | --- | --- |
| All 24 municipalities | In period 23 December 2014 – 16 January 2015 animal feed (for cows, pigs and layers) was delivered to all 24 municipalities. In total, 1,614 agricultural producers received 516,800 kilograms of animal feed for cows, pigs and layers | . |
| All 24 municipalities | Tender of procurement of milking equipment is closed on January 5, 2015. Vendor selection is currently in process. Milking equipment will be purchased and delivered to 25 farming families. | During February 2015 milking equipment will be delivered to milk producers who requested this kind of support to re-start their production. |
| All 24 municipalities | Tender for procurement of spring cropping season is closed on January 10, 2015. More than 7,800 agriculture producers will receive spring crops seed (barley, peas, red clover, lucern and maize). | Spring crops and fertilizer will be delivered to beneficiary families during the period early February till end of March 2015. In terms of number of beneficiaries, this will be the largest group receiving support under the EU flood recovery programme. |